## Cover
GROVE
Iron & Root · Sydney
BUSINESS PLAN · COSTING, BUDGET, TIMELINE & TASKS
Version 1.0 · Confidential · Grove Gym Pty Ltd · hello@thegroveau.com
BUSINESS |  | Grove — Gym, Supplements, Apparel
LOCATION |  | Inner West Sydney
FOUNDERS |  | Jim Thornton & Charlie Foat
OPENING |  | 12 months from today
TOTAL BUDGET |  | $85,000 – $110,000 AUD
MEMBERS CAP |  | 400–450 (hard cap)
BREAK EVEN |  | ~30 members · $2,100/week
CONTACT |  | hello@thegroveau.com
WORKBOOK CONTENTS
01 | Budget Summary |  | Full itemised costs — 7 categories — auto-totalling
02 | Revenue Model |  | 12 month projections + break even analysis
03 | Timeline |  | 6 phases — every task — owner — status
04 | Task Ownership |  | Jim vs Charlie — who leads what
05 | Risk Register |  | 10 risks — likelihood — impact — mitigation
06 | Key Contacts |  | Every professional needed and when
07 | This Week |  | Priority 10 tasks — do these first

## 01 Budget Summary
GROVE — BUDGET SUMMARY (Blue = editable inputs)
COST ITEM | LOW (AUD) | HIGH (AUD) | NOTES
A — BUSINESS SETUP
Pty Ltd registration (ASIC) | 550 | 550 | asic.gov.au — register online
ABN registration | 0 | 0 | Free — abr.business.gov.au
Shareholder agreement — lawyer | 1500 | 3000 | Essential — do this first
Lease review — lawyer | 800 | 1500 | Per lease reviewed
Business bank account | 0 | 0 | Free to open
Accountant setup | 500 | 1000 | Chart of accounts + GST
Insurance — public liability + contents | 3000 | 5000 | Annual premium
SUBTOTAL
B — PROPERTY & FIT-OUT
DA application fee — Inner West Council | 2000 | 5000 | Depends on scope of works
Town planner / DA consultant | 2000 | 4000 | Worth every cent — engage early
Acoustic report — DA requirement | 1500 | 3000 | Required for gym use approval
Structural engineer — floor loading | 1000 | 2000 | Required for heavy equipment
Private certifier — CC + OC | 2000 | 4000 | Faster than council
Rubber flooring — 500sqm | 8000 | 15000 | $16–$30/sqm installed
Lighting — pendant, warm, track | 3000 | 8000 | No fluorescent — ever
Paint + feature wall | 1500 | 3500 | Exposed brick prep
Bathroom upgrade | 3000 | 8000 | If required by DA
Signage — main wall dimensional letters | 3000 | 6000 | Iron or powder-coated steel
Signage — neon / backlit secondary wall | 1500 | 3000 | Sage green LED
Signage — door plate + floor mat | 500 | 1000 | Entry details
Plants — large tropicals + hanging | 2000 | 5000 | One-time investment
Ceiling hanging infrastructure | 500 | 1500 | Structural anchor points
Supplement station / retail display | 1000 | 2500 | Shelving + Grove branding
Reception desk / storage | 1000 | 2500 | Simple, branded
Miscellaneous fit-out contingency | 1000 | 2000 | Always needed
SUBTOTAL
C — EQUIPMENT (Accumulated Over 12 Months)
Cast iron dumbbells 5–60kg full set | 2500 | 5000 | Facebook Marketplace — be patient
Plate-loaded machines — Hammer Strength etc. | 3000 | 8000 | Liquidation auctions — Grays Online
Cable / pulley stations — 2–3 units | 1500 | 4000 | Secondhand commercial grade
Barbells — 6–8 bars | 800 | 2000 | Cast iron preferred
Iron plates — 500kg+ | 1500 | 4000 | The heavier the better
Power rack / squat stands — 1–2 | 500 | 2000 | Solid used rack
Flat / incline / decline benches — 3–4 | 800 | 2000 | Secondhand
Preacher curl bench — 1–2 | 300 | 800 | Old school
Hyperextension bench | 200 | 500
Dip station | 200 | 500
Plate tree / storage — 2–3 | 300 | 800
Miscellaneous small equipment | 500 | 1500
SUBTOTAL
D — TECHNOLOGY & SYSTEMS
Shopify store — Basic plan annual | 588 | 588 | $49/month billed annually
Prestige theme — one time | 320 | 320 | themes.shopify.com
Klaviyo email marketing — annual | 0 | 600 | Free to start
Glofox gym management — annual | 1320 | 1320 | $110/month — member app included
Domain registration — annual | 20 | 50 | thegroveau.com
Google Workspace email — annual | 180 | 300 | hello@thegroveau.com
Access control / door fob system | 1500 | 3500 | Member entry system
CCTV / security system | 800 | 2000 | Basic commercial system
WiFi / internet setup | 500 | 1000 | Business grade NBN
Music system — speakers | 500 | 1500 | Quality matters for vibe
SUBTOTAL
E — BRAND & MARKETING
Logo vectorisation — designer | 300 | 800 | Convert concepts to production files
Business cards — Jim + Charlie | 150 | 300 | MOO premium 400gsm
Founding member cards — 50 cards | 300 | 600 | Premium print + foil
Woven neck labels — 500 units | 200 | 400 | Embroidery supplier
Sleeve patches — 500 units | 300 | 600 | Three lions detail
Photography — brand shoot | 800 | 2000 | Pre-opening content bank
Launch event | 1000 | 3000 | Founding member soft open
Press kit production | 0 | 500 | Write ourselves
Social media tools — CapCut Pro etc. | 200 | 500 | Content creation
SUBTOTAL
F — INVENTORY (Supplements + Apparel)
Opening supplement stock — Emrald Labs | 3000 | 6000 | Negotiate consignment — reduce to $0
Apparel Drop 01 production | 4000 | 8000 | Minimum order quantities
Packaging — bags, tissue, stickers | 300 | 600 | Branded Grove packaging
SUBTOTAL
G — OPERATING RUNWAY (3 Months)
Rent — post rent-free period | 12000 | 18000 | $4,000–$6,000/month
Utilities — power, water, internet | 1500 | 2400 | $500–$800/month
Insurance monthly | 750 | 1200
Software subscriptions | 900 | 1500 | All systems running
Miscellaneous / contingency | 900 | 1500 | Always needed
SUBTOTAL
TOTAL BUDGET |  |  | Realistic target: $85,000–$110,000 AUD
ℹ Blue numbers are editable inputs. Change any figure and subtotals + grand total recalculate automatically.

## 02 Revenue Model
GROVE — REVENUE MODEL · 12 MONTH PROJECTION
PERIOD | MEMBERS | MEMBERSHIP ($) | SUPPLEMENTS ($) | APPAREL ($) | CAMP ($) | OTHER ($) | TOTAL ($)
Pre-Launch M1–M3 | 0 | 0 | 2000 | 3000 | 0 | 0
Pre-Launch M4–M6 | 0 | 0 | 3500 | 4000 | 0 | 0
Soft Open M7 | 50 | 11000 | 4000 | 2000 | 0 | 0
Month 8 | 100 | 28000 | 5000 | 2000 | 0 | 0
Month 9 | 150 | 42000 | 6000 | 3000 | 0 | 0
Month 10 | 200 | 56000 | 7000 | 3000 | 7950 | 0
Month 11 | 300 | 84000 | 8000 | 4000 | 0 | 0
Month 12 | 400 | 112000 | 9000 | 5000 | 7950 | 0
YEAR 1 TOTAL
BREAK EVEN ANALYSIS
SCENARIO | MEMBERS | WEEKLY REV ($) | MONTHLY REV ($) | STATUS
Cover fixed costs only | 30 | 2100 | 8400 | Break even
Costs + equipment finance | 45 | 3150 | 12600 | Sustainable
Comfortable profit | 120 | 8400 | 33600 | Healthy
Strong business | 300 | 21000 | 84000 | Strong
Full capacity — 400–450 members | 400 | 28000 | 112000 | Target

## 03 Timeline
GROVE — 12 MONTH TIMELINE · ALL TASKS
| TASK | TARGET | OWNER | STATUS
PHASE 01 — FOUNDATION · Months 1–2
| Register Pty Ltd company — asic.gov.au | Week 1 | Jim | [ ]
| Register ABN — abr.business.gov.au | Week 1 | Jim | [ ]
| Engage commercial lawyer — shareholder agreement | Week 1 | Jim | [ ]
| Set up hello@thegroveau.com — Google Workspace | Week 1 | Charlie | [ ]
| Register @thegrove.au on all social platforms | Week 1 | Charlie | [ ]
| Open business bank account | Week 2 | Both | [ ]
| Engage accountant — GST setup | Week 2 | Jim | [ ]
| Brief web friend — send Shopify brief document | Week 2 | Charlie | [ ]
| Engage designer — vectorise G monogram + wordmark | Week 2 | Charlie | [ ]
| Print business cards — Jim + Charlie | Week 3 | Charlie | [ ]
| Update Instagram bios — both accounts | Week 1 | Jim | [ ]
| Post comeback — Reminder. — black and white photo | Week 1–2 | Jim | [ ]
| Begin content schedule — 4 posts per week | Week 2+ | Jim | [ ]
PHASE 02 — BUILD THE BRAND · Months 2–4
| Shopify store live — supplements + apparel | Month 2 | Charlie | [ ]
| First Emrald Labs wholesale order placed | Month 2 | Jim | [ ]
| Negotiate consignment / 30-day terms — Emrald Labs | Month 2 | Jim | [ ]
| Founding member pre-registration live on website | Month 2 | Both | [ ]
| Wave 1 founding outreach — 25 private spots | Month 2–3 | Jim | [ ]
| Wave 2 founding launch — public announcement | Month 3 | Jim | [ ]
| Apparel Drop 01 production brief sent | Month 3 | Both | [ ]
| Set up Facebook Marketplace alerts — Inner West | Month 2 | Jim | [ ]
| Register on Grays Online — liquidation auctions | Month 2 | Jim | [ ]
| First equipment purchases begin | Month 2–3 | Jim | [ ]
| Begin warehouse scouting — Marrickville / Sydenham | Month 2 | Both | [ ]
| Engage commercial real estate agent | Month 2–3 | Both | [ ]
| Engage town planner — preliminary DA advice | Month 3 | Jim | [ ]
| Announce Grove concept publicly — Instagram | Month 3 | Jim | [ ]
| TikTok account launched | Month 3 | Charlie | [ ]
PHASE 03 — SECURE THE SPACE · Months 4–6
| Select preferred warehouse property | Month 4 | Both | [ ]
| Engage lawyer to review lease | Month 4 | Jim | [ ]
| Negotiate rent-free period — target 3–6 months | Month 4–5 | Jim | [ ]
| Negotiate DA exit clause in lease | Month 4–5 | Jim | [ ]
| Sign lease | Month 5 | Both | [ ]
| Lodge DA with Inner West Council | Month 5 | Jim | [ ]
| Commission acoustic report | Month 5 | Jim | [ ]
| Commission structural engineer report | Month 5 | Jim | [ ]
| Approach bank — personal income + supplement rev | Month 4–5 | Jim | [ ]
| Apply for business loan / equipment finance | Month 5 | Jim | [ ]
| Target 50–60% of equipment purchased | Month 5–6 | Jim | [ ]
PHASE 04 — BUILD THE SPACE · Months 6–9
| DA approved by Inner West Council | Month 6–7 | Jim | [ ]
| Construction Certificate obtained | Month 7 | Jim | [ ]
| Fit-out contractors briefed | Month 7 | Charlie | [ ]
| Rubber flooring installed | Month 7–8 | Charlie | [ ]
| Lighting installed — warm pendant throughout | Month 7–8 | Charlie | [ ]
| Bathroom upgrade completed | Month 7–8 | Charlie | [ ]
| Grove wall signage fabricated and installed | Month 8 | Charlie | [ ]
| Neon / backlit sign installed | Month 8 | Charlie | [ ]
| Plant ceiling infrastructure installed | Month 8 | Charlie | [ ]
| Supplement station / retail area built | Month 8 | Charlie | [ ]
| All equipment delivered to space | Month 8–9 | Jim | [ ]
| Safety check all equipment | Month 9 | Both | [ ]
| Large tropical plants installed | Month 9 | Both | [ ]
| Occupation Certificate obtained | Month 9 | Jim | [ ]
PHASE 05 — PRE-LAUNCH · Months 9–11
| Glofox gym management system set up | Month 9 | Charlie | [ ]
| Member onboarding process documented | Month 9 | Both | [ ]
| Access control / fob system installed + tested | Month 9–10 | Charlie | [ ]
| All 50 founding members confirmed + payment set up | Month 10 | Jim | [ ]
| Founding member cards printed and ready | Month 10 | Charlie | [ ]
| Standard membership waitlist opened | Month 10 | Both | [ ]
| Apparel Drop 01 received + quality checked | Month 10 | Both | [ ]
| Founding member camp kit assembled | Month 10 | Both | [ ]
| Professional photography + videography shoot | Month 10 | Both | [ ]
| Press kit — pitch Broadsheet, SMH, Men's Health | Month 10–11 | Jim | [ ]
| House rules + member code of conduct documented | Month 10 | Both | [ ]
| Music policy and playlist system set up | Month 10 | Both | [ ]
PHASE 06 — LAUNCH · Month 12
| Founding member exclusive soft open | Week 1 | Both | [ ]
| Photographer / videographer present | Week 1 | Charlie | [ ]
| Every founding member receives card personally | Week 1 | Jim | [ ]
| Supplement brand partners present at launch | Week 1 | Jim | [ ]
| Public opening — social, email, press | Week 2 | Jim | [ ]
| Launch event — community, brands, media | Week 2 | Both | [ ]
| Standard membership applications open | Week 2 | Both | [ ]
| Day pass system active | Week 2 | Charlie | [ ]
| First training camp announced | Week 2 | Jim | [ ]
| Member feedback collected + review | Week 3–4 | Both | [ ]
| First monthly revenue review | Week 4 | Both | [ ]

## 04 Task Ownership
GROVE — TASK OWNERSHIP · JIM vs CHARLIE
AREA | LEAD | SUPPORT | NOTES
Legal & Finance | Jim | Charlie | External lawyer + accountant
Property Scouting | Both | — | Equal responsibility
Equipment Hunting | Jim | — | Jim's industry knowledge and network
Fit-Out Management | Charlie | Jim | Charlie's trade connections
Shopify / Website | Charlie | Web friend | Web friend support for build
Social Media Content | Jim | Charlie | Jim's personal brand drives Grove
Supplement Partnerships | Jim | — | Existing relationships — Emrald Labs
Apparel Production | Both | — | Joint decisions on all pieces
Member Relations | Both | — | Both founders always present
Training Camps | Jim | Charlie | Jim's coaching credibility leads
Brand & Marketing | Both | — | Consistent with brand guidelines
Press & PR | Jim | — | Jim's story drives the narrative
Financial Management | Charlie | Jim | Monthly P&L review together
Operations & Systems | Charlie | Jim | Glofox, Shopify, day to day
Supplement Store | Charlie | Jim | Stock, orders, dispatch

## 05 Risk Register
GROVE — RISK REGISTER
RISK | LIKELIHOOD | IMPACT | MITIGATION
DA refused by council | Medium | High | DA condition in lease. Town planner engaged early. Multiple properties.
Equipment prices higher than expected | Low | Medium | 12-month accumulation. Patience. Secondhand market always has supply.
Founding 50 spots not filled | Low | Medium | Social strategy + personal industry outreach drives pre-registration.
Lease negotiation fails | Medium | Medium | Multiple properties identified. Not locked to one space.
Fit-out costs exceed budget | Medium | High | Detailed contractor quote before signing lease. Contingency built in.
Key supplier relationship changes | Low | Medium | Written agreement with Emrald Labs. Multiple supplier options.
Social growth slower than projected | Medium | Low | Founding members not dependent on follower count.
Bank loan not approved | Low | Medium | Personal income strong at $125k. Multiple funding sources.
Opening delayed beyond 12 months | Medium | Medium | Founding members on rolling weekly — not tied to open date.
Jim or Charlie unavailable | Low | High | Shareholder agreement covers roles, equity, and exit scenarios.

## 06 Key Contacts
GROVE — KEY CONTACTS TO ESTABLISH
ROLE | WHY NEEDED | WHEN | STATUS
Commercial Lawyer — Sydney | Pty Ltd, shareholder agreement, lease review | This week | [ ] Not started
Accountant — small biz Sydney | Setup, GST, tax structure, P&L | This week | [ ] Not started
Commercial RE Agent — Inner West | Property search — Marrickville / Sydenham | Month 2 | [ ] Not started
Town Planner — Inner West area | DA advice before lease signed | Month 3 | [ ] Not started
Private Certifier | Construction Certificate + OC | Month 5 | [ ] Not started
Acoustic Consultant | DA requirement — gym noise report | Month 5 | [ ] Not started
Structural Engineer | Floor loading for heavy iron equipment | Month 5 | [ ] Not started
Fit-Out Contractor | Flooring, lighting, walls | Month 6 | [ ] Not started
Signage Fabricator | Dimensional iron letters, neon sign | Month 7 | [ ] Not started
Plant Supplier — wholesale | Large tropicals, hanging plants bulk | Month 8 | [ ] Not started
Embroidery Supplier | Woven neck labels, sleeve patches | Month 3 | [ ] Not started
Apparel Manufacturer | Drop 01 — tees, hoodies, shorts, caps | Month 3 | [ ] Not started
Photographer / Videographer | Content bank + launch shoot | Month 9 | [ ] Not started
Glofox / TeamUp Rep | Gym management system setup | Month 9 | [ ] Not started
Emrald Labs Contact | Wholesale pricing, consignment terms | Month 2 | ✅ Relationship exists

## 07 This Week
GROVE — THIS WEEK · PRIORITY 10 TASKS · DO THESE FIRST
# | TASK | WHO | BY | STATUS
1 | Register Pty Ltd — asic.gov.au | Jim | Day 1 | [ ] Not done
2 | Register ABN — abr.business.gov.au | Jim | Day 1 | [ ] Not done
3 | Call commercial lawyer — book appointment | Jim | Day 1 | [ ] Not done
4 | Set up Google Workspace — hello@thegroveau.com | Charlie | Day 2 | [ ] Not done
5 | Update Instagram bios — @jimthornton + @thegrove.au | Jim | Day 2 | [ ] Not done
6 | Post Reminder. comeback — black and white training photo | Jim | Day 3 | [ ] Not done
7 | Set up Shopify account using Grove Gmail | Charlie | Day 3 | [ ] Not done
8 | Brief web friend — send Shopify brief document | Charlie | Day 4 | [ ] Not done
9 | Set up Facebook Marketplace + Gumtree equipment alerts | Jim | Day 4 | [ ] Not done
10 | Register @thegrove.au on TikTok, YouTube, Facebook | Charlie | Day 5 | [ ] Not done
These 10 tasks unlock everything else. Nothing moves until these are done. Romans 8:18 · Iron & Root · Sydney